## Sheet1
SAPTHAGIRI COLLEGE OF ENGINEERING
(Affiliated to Visvesvaraya Technological University, Belagavi & Approved by AICTE, New Delhi)
#14/5, Chikkasandra, Hesaraghatta Main Road, Bengaluru – 560057
Phone:080-28372800/1/2 www.sapthagiri.edu.in Fax: 080-28372797
Internal Quality Assurance Cell
Strategic Perspective Plan for the IQAC Year 2014-15
Sl. No. | Chronology | Plan | Description | Strategy | Funds/Budget | Remarks
1 | June5, 2014 | Quality Process initiation | Issues Circular to all Heads for preparation of Time table and Master Time Table, Perspective Plan of each department and Cell, Curriculum Plan, Deployment template, Staff requirement and workload, Bridge Course curriculum and other activities | Issue circulars and follow up. | Refreshments/stationery
Set deadlines
2 | June 7, 2014 | Consolidating Workload & Faculty Requitrement of each department | Collect all Workload & Faculty Requirement of all the departments | Inform GC about the faculty requirement of the college and requesting them to initiate the process | Refreshments/stationery
3 | June 23, 2014 | Consolidating the SPP of the College and deployment strategy | Collect all SPPs, brainstorm in the IQAC and seek the approval of the GC through the Principal and implement | Explain to GC and get approval and also get budget approvals | Consolidating budgetary requirements as per the SPPs of each Dept. and each Cell
4 | June 25, 2014 | Organizing Orientation to staff on Blooms Taxonomy | Mr. xxx will be invited to conduct Orientation Program to facilitate the implementation of Blooms Taxonomy | 1. Coordinate the event | 1. Rs. 10,000/- towards the Honararium &, logistics, Refreshments etc. | IQAC to form various groups for the purpose
2. date and time,
3. Preparation for implementation of Blooms taxonomy in the curriculum
5 | Jan 27, 2015 | Cosolidate the CPD of all the departments and to submit report for odd semester | Collect the odd semester report of each departments,committees etc. Collect workload and CPD of all subjects in each department for the next semester and sending it to GC for kind informatio | Inform GC about the Progress made in the odd semester of 2014-15 and any additional requirement for the coming semester | Refreshments/stationery
6 | May 12, 2015 | To conduct a FDP | Planned to conduct an FDP on emerging trends in Engineering & technology | 1. Coordinate the event | 1. Rs. 10,000/- towards the Honararium &, logistics, Refreshments etc.
2. date and time,
3. Preparation for implementation of Blooms taxonomy in the curriculum
7 | June 5, 2015 | Consolidate the reports of all the departments and committees | Collect all the reports from Depatments & committees prepare final report | The Final college annual report for the academic year 2014-15 to be submitted to GC | Refreshments/stationery
|  | Coordinator |  |  | Principal